NAVIS

# Team Development & Integration Plan

Four-person ownership, 36-hour MVP sprint, milestones and Git workflow

Version 1.0 | 31 October 2026

Architecture baseline: laptop-hosted AI processing; hybrid smartphone/wearable audio; Wi-Fi camera and sensor communication.

# 1. Team structure

| Role | Ownership | Core deliverables |
| --- | --- | --- |
| Member 1 - Embedded Systems | ESP32-CAM, VL53L0X, I2C, Wi-Fi, firmware | Working wearable sensing hardware and telemetry |
| Member 2 - AI & Computer Vision | YOLO26, Nemotron, scene analysis, hazard engine | Object detection, visual reasoning and local safety logic |
| Member 3 - Android Engineer | Kotlin, Compose, voice, TTS, Bluetooth, GPS | Accessible Android companion and hybrid audio |
| Member 4 - Integration & Backend | FastAPI, API contracts, WebSocket, device sessions, integration | Connected end-to-end system and shared technical docs |

# 2. Responsibility matrix

| Module | M1 | M2 | M3 | M4 |
| --- | --- | --- | --- | --- |
| ESP32-CAM | Lead | Support |  | Support |
| VL53L0X | Lead | Support |  | Support |
| Wi-Fi firmware | Lead |  |  | Support |
| YOLO26 |  | Lead |  | Support |
| Nemotron |  | Lead |  | Support |
| Hazard engine | Support | Lead | Support | Support |
| FastAPI |  | Support |  | Lead |
| WebSocket |  | Support | Support | Lead |
| Android UI |  |  | Lead | Support |
| Voice and Bluetooth |  |  | Lead | Support |
| Integration testing | Support | Support | Support | Lead |

# 3. Integration rules

All team members use the shared API contracts and field names.

Member 1 provides sample images and sensor JSON early; do not wait for full firmware.

Member 2 exposes stable detection and scene APIs; use mock inputs while hardware is being completed.

Member 3 builds against mock API responses while backend work proceeds.

Member 4 owns integration, API versioning, test environment and merge coordination.

Every module must have a local test before end-to-end integration.

Changes to API schemas require documentation updates and team notification.

# 4. 36-hour sprint

| Time | Focus | Expected milestone |
| --- | --- | --- |
| 0–4 h | Repo, architecture, environments, contracts | Project scaffolding |
| 4–10 h | Camera upload, ToF init, YOLO loading, Compose shell, FastAPI | First image reaches AI server |
| 10–16 h | Sensor telemetry, detection JSON, hazard engine, voice pipeline, WebSocket | Object detection and proximity alert |
| 16–22 h | Nemotron, scene description, Android command integration | Spoken visual Q&A |
| 22–27 h | Bluetooth routing, wake word, alert interruption, accessibility | Hybrid audio assistant |
| 27–32 h | Physical integration and end-to-end testing | Complete prototype |
| 32–36 h | Failure tests, demo script, presentation, backup recording | Demonstrable MVP |

# 5. Post-MVP roadmap

| Period | Focus |
| --- | --- |
| Week 1 | Improve detection, scene grounding and latency |
| Week 2 | OCR and document reading |
| Week 3 | Google Maps destination search and voice navigation |
| Week 4 | Emergency workflow, privacy and security |
| Week 5 | Supervised accessibility testing and hardware refinement |

# 6. Repository structure

NAVIS/
  android/navis-android/
  firmware/esp32-cam/
  backend/navis-backend/
  docs/ (PRD, TRD, API, architecture, wiring, testing, team allocation)
  assets/ (diagrams, UI, demo)
  README.md
  .gitignore

# 7. Git workflow

| Branch | Purpose |
| --- | --- |
| main | Stable tested release |
| develop | Integrated development |
| feature/firmware | ESP32 work |
| feature/ai-engine | Vision and AI work |
| feature/android | Android work |
| feature/backend | FastAPI and integration work |

Feature branches are merged into develop through pull requests. Only tested, integrated versions should be promoted to main.

# 8. Milestones

| Milestone | Deliverable | Owner |
| --- | --- | --- |
| M1 | Working ESP32 camera | M1 |
| M2 | ToF telemetry | M1 |
| M3 | YOLO26 inference | M2 |
| M4 | Hazard engine | M2 |
| M5 | FastAPI endpoints | M4 |
| M6 | Nemotron integration | M2 |
| M7 | Android voice assistant | M3 |
| M8 | Bluetooth audio routing | M3 |
| M9 | WebSocket integration | M4 |
| M10 | Complete wearable demonstration | All |

# 9. Final demo scenario

User says “Hello NAVIS”; assistant responds.

User asks for surroundings; camera frame is processed and scene is described.

User asks a follow-up about an object; assistant uses context and current visual evidence.

ToF sensor reports a close object; urgent alert interrupts ordinary speech.

User asks to read a sign; OCR reads text (if Phase 2 is implemented).

Demonstrate phone/wearable audio switching and a connection failure fallback.

# 10. Safety and demo rules

Do not conduct unsupervised mobility tests. Keep a white cane or usual mobility aid available. Use controlled test obstacles and a sighted safety observer. Clearly disclose that the prototype can miss obstacles and is not a collision-avoidance or autonomous navigation device.